## Example 3.1
Example 3.1 - Single Time Estimate
Immediate Predecessors
Activity | Time | P1 | P2 |  | In this example, each path through the network is identified and evaluated. The time for a path is the total time for all activities in the path. The path with the longest time is the "CRITICAL PATH." In this example there are two critical pathes (A-B-D-E-G) and (A-C-E-G).
A | 21
B | 5 | A
C | 7 | A
D | 2 | B
E | 5 | C | D
F | 8 | C | D
G | 2 | E | F
Activities in Path
Path | 1 | 2 | 3 | 4 | 5
1 | A | B | D | E | G
2 | A | B | D | F | G
3 | A | C | E | G
4 | A | C | F | G
Activity Times
Path | 1 | 2 | 3 | 4 | 5 | Total
1 | 21 | 5 | 2 | 8 | 2 | 38 | = Critical Path
2 | 21 | 5 | 2 | 5 | 2 | 35
3 | 21 | 7 | 8 | 2 |  | 38 | = Critical Path
4 | 21 | 7 | 5 | 2 |  | 35

## Ex. 3.2-Exh. 3.6
Example 3.2 Three Time Estimates
Activity | Activity Designation | Time Estimates |  |  | Expected Time | Activity Variance | Immediate Predecessors
|  | a | m | b |  |  | P1 | P2
Design | A | 10 | 22 | 28 | 21 | 9
Build prototype | B | 4 | 4 | 10 | 5 | 1 | A
Evaluate equipment | C | 4 | 6 | 14 | 7 | 2.7778 | A
Test prototype | D | 1 | 2 | 3 | 2 | 0.11111 | B
Write report | E | 1 | 5 | 9 | 5 | 1.7778 | C | D
Write methods report | F | 7 | 8 | 9 | 8 | 0.11111 | C | D
Write final report | G | 2 | 2 | 2 | 2 | 0 | E | F
| Activity Designation | Expected Time | Earliest Start | Earliest Finish | Latest Finish | Latest Start | Slack Time | Activity Variance
| A | 21 | 0 | 21 | 21 | 0 | 0 | 9
| B | 5 | 21 | 26 | 26 | 21 | 0
| C | 7 | 21 | 28 | 28 | 21 | 0 | 2.7778
| D | 2 | 26 | 28 | 28 | 26 | 0
| E | 5 | 28 | 33 | 36 | 31 | 3
| F | 8 | 28 | 36 | 36 | 28 | 0 | 0.11111
| G | 2 | 36 | 38 | 38 | 36 | 0 | 0
| 11.8889 | = Variance of Critical Path
| 3.448 | = Std. Deviation of Critical Path |  |  |  |  | = indicates Critical path
| 35 | = Project Due Date
| -0.87006 | = Calculated Z-value
| 0.19213 | = Probability of On-Time Completion
Note on G24: Since G has the largest "Earliest Finish" time, its "Latest Finish" time is equal to its "Earliest Finish" time.
Note on D16: Expected time is based on the three time estimates.
Note on E18: The "Earlist Start" time for the first activity is always equal to zero.
Note on E16: The "Earliest Start" time is the minimum time delay before starting the activity. The "Earliest Start" time is determined by the "Latest Finish" time of its predeccessors.
Note on F16: The "Earliest Finish" time is the minimum time delay to complete the activity. The "Earliest Finish" time equals the "Earliest Start" time plus the expected activity time.
Note on G16: The "Latest Finish" time is the maximum time delay before starting the activity without delaying the project. The "Latest Finish" time equals the "Latest Start" time minus the expected activity time.
Note on H16: The "Latest Start" time is maximum time delay before finishing the activity without delaying the project. The "Latest Start" time is determined by the "Latest Finish" time of its predecessors.
Note on D5: Optimistic time
Note on E5: Most Likely Time
Note on F5: Pessimistic Time

## Exhibit 3.8
Exhibit 3.8 - Time-Cost Trade-off Example
Activity Designation | Normal Time | Crash Time | Normal Cost | Crash Cost
A | 2 | 1 | 6 | 10 |  |  | = Crashed
B | 5 | 2 | 9 | 18 |  |  | = Critical Path
C | 4 | 3 | 6 | 8
D | 3 | 1 | 5 | 9
Activity Designation | Earliest Start | Earliest Finish | Latest Finish | Latest Start | Slack Time | Activity Cost | Days Crashed
A | 0 | 2 | 0 | 2 | 0 | 6 | 0
B | 2 | 7 | 2 | 7 | 0 | 9 | 0
C | 2 | 6 | 3 | 7 | 1 | 6 | 0
D | 7 | 10 | 7 | 10 | 0 | 5 | 0
[5 empty] | Total Project Cost = | 26
[5 empty] | Time To Complete Project = | 10
Note on C12: The "Earliest Start" time is the minimum time delay before starting the activity. The "Earliest Start" time is determined by the "Latest Finish" time of its predeccessors.
Note on D12: The "Earliest Finish" time is the minimum time delay to complete the activity. The "Earliest Finish" time equals the "Earliest Start" time plus the expected activity time.
Note on E12: The "Latest Finish" time is the maximum time delay before starting the activity without delaying the project. The "Latest Finish" time equals the "Latest Start" time minus the expected activity time.
Note on F12: The "Latest Start" time is maximum time delay before finishing the activity without delaying the project. The "Latest Start" time is determined by the "Latest Finish" time of its predecessors.
Note on C13: The "Earlist Start" time for the first activity is always equal to zero.
Note on C4: Normal time to complete activity.
Note on E4: Activity cost for normal time
Note on D4: Time to complete activity when crashed.
Note on F4: Cost for activity when crashed.