## Chapter 17
Templates to accompany Operations Management, Seventh Edition
created by Lee Tangedahl, The University of Montana
Copyright © 2001 by The McGraw Hill Companies, Inc.
All rights Reserved.
Chapter Seventeen - Scheduling
| Templates: | Assignment Model
Job Sequencing
Johnson's Rule
Examples
Solved Problems
See Instructions template for complete instructions.

## Assignment
Assignment Model |  |  | Notes
Input Matrix: |  |  | Machine
|  |  | A | B | C | D | E
| Job | 1 | 8 | 6 | 2 | 4 |  | 1
|  | 2 | 6 | 7 | 11 | 10 |  | 1
|  | 3 | 3 | 5 | 7 | 6 |  | 1
|  | 4 | 5 | 10 | 12 | 9 |  | 1
|  | 5 | [5 empty] | 0
|  |  | 1 | 1 | 1 | 1 | 0
[9 empty] | Total Jobs = | 4
[9 empty] | Total Machines = | 4
Solution Matrix: |  |  | Machine
|  |  | A | B | C | D | E
| Job | 1 | 0 | 0 | 1 | 0 | 0 | 1
|  | 2 | 0 | 1 | 0 | 0 | 0 | 1
|  | 3 | 0 | 0 | 0 | 1 | 0 | 1
|  | 4 | 1 | 0 | 0 | 0 | 0 | 1
|  | 5 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1 | 1 | 1 | 1 | 0
[9 empty] | Total Cost = | 20
Notes: | 1. | The Solver Add-in must be available, use Tools Add-In and select Solver if necessary.
| 2. | Enter costs in Input Matrix.
| 3. | You can be manually enter values in the Solution Matrix or you may press Solve for optimal solution.
If the number of machines exceeds the number of jobs, you must enter a Dummy job with costs of zero.
Small numbers in scientific notation (e.g. 2.4091E-11) reflects the precision of Solver and can be treated as zero.
Back

## Job Sequencing
Notes
|  |  | Current Date: | 0
| Process. | Due | Remain | CR | Critical |  |  | Flow | Days | A | 0
Job | Time | Date | Oper. | Sequence | Ratio | Slack | S/O | Time | Late | B | 0
A | 2 | 7 |  |  | 3.5 | 5 |  | 2 | 0 | C | 10
B | 8 | 16 |  |  | 2 | 8 |  | 10 | 0 | D | 7
C | 4 | 4 |  |  | 1 | 0 |  | 14 | 10 | E | 14
D | 10 | 17 |  |  | 1.7 | 7 |  | 24 | 7 | F | 23
E | 5 | 15 |  |  | 3 | 10 |  | 29 | 14
F | 12 | 18 |  |  | 1.5 | 6 |  | 41 | 23
Totals | 41 |  | 0 |  |  | 36 |  | 120 | 54
Method |  |  | FCFS
Average Flow Time |  |  | 20
Average Tardiness |  |  | 9
Average Number of Jobs |  |  | 2.9268
See notes below.
Notes:
1. | Enter Job Name, Processing Time, and Due Date for each job.
2. | For the FCFS, SPT, and DD rules, simply press the appropriate button.
3. | For the CR rule, perform the following BEFORE pressing the CR button:
| a. | Select job with lowest Critical Ratio
| b. | Schedule that job next by entering next sequence number (start with 1) in the
CR Sequence cloumn.
| c. | Add the processing time for that job to the current date.
| d. | Repeat steps a, b, and c until all jobs have been schduled (i.e. the CR
Sequence column is filled in).
| e. | Then press the CR button.
4. | Fill in the Remaining Operations column and then press the S/O button.
Back

## Johnson's Rule
Johnson's Rule
Step 1 - Fill in jobs and times: |  |  |  |  | Resulting schedule:
| Job | Time1 | Time2 |  | Job | Start 1 | Done 1 | Start 2 | Done 2 | Idle 2
| A | 5 | 5 |  | D | 0 | 2 | 2 | 9 | 2
| B | 4 | 3 |  | E | 2 | 8 | 9 | 17 | 0
| C | 8 | 9 |  | C | 8 | 16 | 17 | 26 | 0
| D | 2 | 7 |  | F | 16 | 28 | 28 | 43 | 2
| E | 6 | 8 |  | A | 28 | 33 | 43 | 48 | 0
| F | 12 | 15 |  | B | 33 | 37 | 48 | 51 | 0
[6 empty] | 37 | 37 | 51 | 51 | 0
[5 empty] | Idle time-> |  | 14 |  |  | 4
Step 2 - Assign job order:
| A |  |  | D | E | C | F | A | B
B
C
D
E
F

## Examples
Chapter 17 - Examples
1. | Assignment Model
| Input Matrix: |  |  | Machine
|  |  |  | A | B | C | D | E
|  | Job | 1 | 8 | 6 | 2 | 4 |  | 1
|  |  | 2 | 6 | 7 | 11 | 10 |  | 1
|  |  | 3 | 3 | 5 | 7 | 6 |  | 1
|  |  | 4 | 5 | 10 | 12 | 9 |  | 1
|  |  | 5 | [5 empty] | 0
|  |  |  | 1 | 1 | 1 | 1 | 0
[10 empty] | Total Jobs = | 4
[10 empty] | Total Machines = | 4
| Solution Matrix: |  |  | Machine
|  |  |  | A | B | C | D | E
|  | Job | 1 | 0 | 0 | 1 | 0 | 0 | 1
|  |  | 2 | 0 | 1 | 0 | 0 | 0 | 1
|  |  | 3 | 0 | 0 | 0 | 1 | 0 | 1
|  |  | 4 | 1 | 0 | 0 | 0 | 0 | 1
|  |  | 5 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1 | 1 | 1 | 1 | 0
[10 empty] | Total Cost = | 20
2. | Job Sequencing
| FCFS: |  | Process. | Due | Remain | Critical |  |  | Flow | Days
|  | Job | Time | Date | Oper. | Ratio | Slack | S/O | Time | Late
|  | A | 2 | 7 |  | 3.5 | 5 |  | 2 | 0
|  | B | 8 | 16 |  | 2 | 8 |  | 10 | 0
|  | C | 4 | 4 |  | 1 | 0 |  | 14 | 10
|  | D | 10 | 17 |  | 1.7 | 7 |  | 24 | 7
|  | E | 5 | 15 |  | 3 | 10 |  | 29 | 14
|  | F | 12 | 18 |  | 1.5 | 6 |  | 41 | 23
|  | Totals | 41 |  | 0 |  | 36 |  | 120 | 54
|  | Method |  |  | FCFS
|  | Average Flow Time |  |  | 20
|  | Average Tardiness |  |  | 9
|  | Average Number of Jobs |  |  | 2.9268
| SPT: |  | Process. | Due | Remain | Critical |  |  | Flow | Days
|  | Job | Time | Date | Oper. | Ratio | Slack | S/O | Time | Late
|  | A | 2 | 7 |  | 3.5 | 5 |  | 2 | 0
|  | C | 4 | 4 |  | 1 | 0 |  | 6 | 2
|  | E | 5 | 15 |  | 3 | 10 |  | 11 | 0
|  | B | 8 | 16 |  | 2 | 8 |  | 19 | 3
|  | D | 10 | 17 |  | 1.7 | 7 |  | 29 | 12
|  | F | 12 | 18 |  | 1.5 | 6 |  | 41 | 23
|  | Totals | 41 |  | 0 |  | 36 |  | 108 | 40
|  | Method |  |  | SPT
|  | Average Flow Time |  |  | 18
|  | Average Tardiness |  |  | 6.6667
|  | Average Number of Jobs |  |  | 2.6341
| DD: |  | Process. | Due | Remain | Critical |  |  | Flow | Days
|  | Job | Time | Date | Oper. | Ratio | Slack | S/O | Time | Late
|  | C | 4 | 4 |  | 1 | 0 |  | 4 | 0
|  | A | 2 | 7 |  | 3.5 | 5 |  | 6 | 0
|  | E | 5 | 15 |  | 3 | 10 |  | 11 | 0
|  | B | 8 | 16 |  | 2 | 8 |  | 19 | 3
|  | D | 10 | 17 |  | 1.7 | 7 |  | 29 | 12
|  | F | 12 | 18 |  | 1.5 | 6 |  | 41 | 23
|  | Totals | 41 |  | 0 |  | 36 |  | 110 | 38
|  | Method |  |  | DD
|  | Average Flow Time |  |  | 18.3333
|  | Average Tardiness |  |  | 6.3333
|  | Average Number of Jobs |  |  | 2.6829
| CR: |  |  |  | Current Date: | 0
|  |  | Process. | Due | Remain | CR | Critical |  |  | Flow | Days
|  | Job | Time | Date | Oper. | Sequence | Ratio | Slack | S/O | Time | Late
|  | A | 2 | 7 |  |  | 3.5 | 5 |  | 2 | 0
|  | B | 8 | 16 |  |  | 2 | 8 |  | 10 | 0
|  | C | 4 | 4 |  |  | 1 | 0 |  | 14 | 10
|  | D | 10 | 17 |  |  | 1.7 | 7 |  | 24 | 7
|  | E | 5 | 15 |  |  | 3 | 10 |  | 29 | 14
|  | F | 12 | 18 |  |  | 1.5 | 6 |  | 41 | 23
|  | Totals | 41 |  | 0 |  |  | 36 |  | 120 | 54
[5 empty] | Current Date: | 4
|  |  | Process. | Due | Remain | CR | Critical |  |  | Flow | Days
|  | Job | Time | Date | Oper. | Sequence | Ratio | Slack | S/O | Time | Late
|  | A | 2 | 7 |  |  | 1.5 | 5 |  | 2 | 0
|  | B | 8 | 16 |  |  | 1.5 | 8 |  | 10 | 0
|  | C | 4 | 4 |  | 1 |  | 0 |  | 14 | 10
|  | D | 10 | 17 |  |  | 1.3 | 7 |  | 24 | 7
|  | E | 5 | 15 |  |  | 2.2 | 10 |  | 29 | 14
|  | F | 12 | 18 |  |  | 1.1667 | 6 |  | 41 | 23
|  | Totals | 41 |  | 0 |  |  | 36 |  | 120 | 54
[5 empty] | Current Date: | 16
|  |  | Process. | Due | Remain | CR | Critical |  |  | Flow | Days
|  | Job | Time | Date | Oper. | Sequence | Ratio | Slack | S/O | Time | Late
|  | A | 2 | 7 |  |  | -4.5 | 5 |  | 2 | 0
|  | B | 8 | 16 |  |  | 0 | 8 |  | 10 | 0
|  | C | 4 | 4 |  | 1 |  | 0 |  | 14 | 10
|  | D | 10 | 17 |  |  | 0.1 | 7 |  | 24 | 7
|  | E | 5 | 15 |  |  | -0.2 | 10 |  | 29 | 14
|  | F | 12 | 18 |  | 2 |  | 6 |  | 41 | 23
|  | Totals | 41 |  | 0 |  |  | 36 |  | 120 | 54
[5 empty] | Current Date: | 18
|  |  | Process. | Due | Remain | CR | Critical |  |  | Flow | Days
|  | Job | Time | Date | Oper. | Sequence | Ratio | Slack | S/O | Time | Late
|  | A | 2 | 7 |  | 3 |  | 5 |  | 2 | 0
|  | B | 8 | 16 |  |  | -0.25 | 8 |  | 10 | 0
|  | C | 4 | 4 |  | 1 |  | 0 |  | 14 | 10
|  | D | 10 | 17 |  |  | -0.1 | 7 |  | 24 | 7
|  | E | 5 | 15 |  |  | -0.6 | 10 |  | 29 | 14
|  | F | 12 | 18 |  | 2 |  | 6 |  | 41 | 23
|  | Totals | 41 |  | 0 |  |  | 36 |  | 120 | 54
[5 empty] | Current Date: | 23
|  |  | Process. | Due | Remain | CR | Critical |  |  | Flow | Days
|  | Job | Time | Date | Oper. | Sequence | Ratio | Slack | S/O | Time | Late
|  | A | 2 | 7 |  | 3 |  | 5 |  | 2 | 0
|  | B | 8 | 16 |  |  | -0.875 | 8 |  | 10 | 0
|  | C | 4 | 4 |  | 1 |  | 0 |  | 14 | 10
|  | D | 10 | 17 |  |  | -0.6 | 7 |  | 24 | 7
|  | E | 5 | 15 |  | 4 |  | 10 |  | 29 | 14
|  | F | 12 | 18 |  | 2 |  | 6 |  | 41 | 23
|  | Totals | 41 |  | 0 |  |  | 36 |  | 120 | 54
[5 empty] | Current Date: | 23
|  |  | Process. | Due | Remain | CR | Critical |  |  | Flow | Days
|  | Job | Time | Date | Oper. | Sequence | Ratio | Slack | S/O | Time | Late
|  | A | 2 | 7 |  | 3 |  | 5 |  | 2 | 0
|  | B | 8 | 16 |  | 4 |  | 8 |  | 10 | 0
|  | C | 4 | 4 |  | 1 |  | 0 |  | 14 | 10
|  | D | 10 | 17 |  | 5 |  | 7 |  | 24 | 7
|  | E | 5 | 15 |  | 4 |  | 10 |  | 29 | 14
|  | F | 12 | 18 |  | 2 |  | 6 |  | 41 | 23
|  | Totals | 41 |  | 0 |  |  | 36 |  | 120 | 54
Press CR Button
|  |  | Process. | Due | Remain | CR | Critical |  |  | Flow | Days
|  | Job | Time | Date | Oper. | Sequence | Ratio | Slack | S/O | Time | Late
|  | C | 4 | 4 |  | 1 |  | 0 |  | 4 | 0
|  | F | 12 | 18 |  | 2 |  | 6 |  | 16 | 0
|  | A | 2 | 7 |  | 3 |  | 5 |  | 18 | 11
|  | B | 8 | 16 |  | 4 |  | 8 |  | 26 | 10
|  | E | 5 | 15 |  | 4 |  | 10 |  | 31 | 16
|  | D | 10 | 17 |  | 5 |  | 7 |  | 41 | 24
|  | Totals | 41 |  | 0 |  |  | 36 |  | 136 | 61
|  | Method |  |  | CR
|  | Average Flow Time |  |  | 22.6667
|  | Average Tardiness |  |  | 10.1667
|  | Average Number of Jobs |  |  | 3.3171
3. | Job Sequencing
|  |  | Process. | Due | Remain | Critical |  |  | Flow | Days
|  | Job | Time | Date | Oper. | Ratio | Slack | S/O | Time | Late
|  | C | 8 | 8 | 5 | 1 | 0 | 0 | 8 | 0
|  | B | 16 | 32 | 6 | 2 | 16 | 2.6667 | 24 | 0
|  | A | 4 | 14 | 3 | 3.5 | 10 | 3.3333 | 28 | 14
|  | E | 10 | 30 | 4 | 3 | 20 | 5 | 38 | 8
|  | F | 18 | 30 | 2 | 1.6667 | 12 | 6 | 56 | 26
|  | D | 20 | 34 | 2 | 1.7 | 14 | 7 | 76 | 42
|  | Totals | 76 |  | 22 |  | 72 |  | 230 | 90
|  | Method |  |  | S/O
|  | Average Flow Time |  |  | 38.3333
|  | Average Tardiness |  |  | 15
|  | Average Number of Jobs |  |  | 3.0263
4. | Johnson's Rule
| Step 1 - Fill in jobs and times: | [5 empty] | Resulting schedule:
|  | Job | Time1 | Time2 |  |  | Job | Start 1 | Done 1 | Start 2 | Done 2 | Idle 2
|  | A | 5 | 5 |  |  | D | 0 | 2 | 2 | 9 | 2
|  | B | 4 | 3 |  |  | E | 2 | 8 | 9 | 17 | 0
|  | C | 8 | 9 |  |  | C | 8 | 16 | 17 | 26 | 0
|  | D | 2 | 7 |  |  | F | 16 | 28 | 28 | 43 | 2
|  | E | 6 | 8 |  |  | A | 28 | 33 | 43 | 48 | 0
|  | F | 12 | 15 |  |  | B | 33 | 37 | 48 | 51 | 0
[8 empty] | 37 | 37 | 51 | 51 | 0
[7 empty] | Idle time-> |  | 14 |  |  | 4
Step 2 - Assign job order:
|  | A |  |  |  | D | E | C | F | A | B
B
C
D
E
F

## Solved Problems
Chapter 17 - Solved Problems
1. | Assignment Model
| Input Matrix: |  |  | Machine
|  |  |  | A | B | C | D | E
|  | Job | 1 | 12 | 16 | 14 | 10 |  | 1
|  |  | 2 | 9 | 8 | 13 | 7 |  | 1
|  |  | 3 | 15 | 12 | 9 | 11 |  | 1
|  |  | 4 | 0 | 0 | 0 | 0 |  | 1
|  |  | 5 | [5 empty] | 0
|  |  |  | 1 | 1 | 1 | 1 | 0
[10 empty] | Total Jobs = | 4
[10 empty] | Total Machines = | 4
| Solution Matrix: |  |  | Machine
|  |  |  | A | B | C | D | E
|  | Job | 1 | 0 | 0 | 0 | 1 | 0 | 1
|  |  | 2 | 0 | 1 | 0 | 0 | 0 | 1
|  |  | 3 | 0 | 0 | 1 | 0 | 0 | 1
|  |  | 4 | 1 | 0 | 0 | 0 | 0 | 1
|  |  | 5 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1 | 1 | 1 | 1 | 0
[10 empty] | Total Cost = | 27
2. | Job Sequencing
| SPT: |  | Process. | Due | Remain | Critical |  |  | Flow | Days
|  | Job | Time | Date | Oper. | Ratio | Slack | S/O | Time | Late
|  | d | 3 | 8 |  | 2.6667 | 5 |  | 3 | 0
|  | b | 6 | 24 |  | 4 | 18 |  | 9 | 0
|  | e | 7 | 6 |  | 0.85714 | -1 |  | 16 | 10
|  | a | 12 | 15 |  | 1.25 | 3 |  | 28 | 13
|  | c | 14 | 20 |  | 1.4286 | 6 |  | 42 | 22
|  | Totals | 42 |  | 0 |  | 31 |  | 98 | 45
|  | Method |  |  | SPT
|  | Average Flow Time |  |  | 19.6
|  | Average Tardiness |  |  | 9
|  | Average Number of Jobs |  |  | 2.3333
| DD: |  | Process. | Due | Remain | Critical |  |  | Flow | Days
|  | Job | Time | Date | Oper. | Ratio | Slack | S/O | Time | Late
|  | e | 7 | 6 |  | 0.85714 | -1 |  | 7 | 1
|  | d | 3 | 8 |  | 2.6667 | 5 |  | 10 | 2
|  | a | 12 | 15 |  | 1.25 | 3 |  | 22 | 7
|  | c | 14 | 20 |  | 1.4286 | 6 |  | 36 | 16
|  | b | 6 | 24 |  | 4 | 18 |  | 42 | 18
|  | Totals | 42 |  | 0 |  | 31 |  | 117 | 44
|  | Method |  |  | DD
|  | Average Flow Time |  |  | 23.4
|  | Average Tardiness |  |  | 8.8
|  | Average Number of Jobs |  |  | 2.7857
| CR: |  |  |  | Current Day: | 0
|  |  | Process. | Due | Remain | CR | Critical |  |  | Flow | Days
|  | Job | Time | Date | Oper. | Sequence | Ratio | Slack | S/O | Time | Late
|  | a | 12 | 15 |  |  | 1.25 | 3 |  | 12 | 0
|  | b | 6 | 24 |  |  | 4 | 18 |  | 18 | 0
|  | c | 14 | 20 |  |  | 1.4286 | 6 |  | 32 | 12
|  | d | 3 | 8 |  |  | 2.6667 | 5 |  | 35 | 27
|  | e | 7 | 6 |  |  | 0.85714 | -1 |  | 42 | 36
|  | Totals | 42 |  | 0 |  |  | 31 |  | 139 | 75
[5 empty] | Current Day: | 7
|  |  | Process. | Due | Remain | CR | Critical |  |  | Flow | Days
|  | Job | Time | Date | Oper. | Sequence | Ratio | Slack | S/O | Time | Late
|  | a | 12 | 15 |  |  | 0.66667 | 3 |  | 12 | 0
|  | b | 6 | 24 |  |  | 2.8333 | 18 |  | 18 | 0
|  | c | 14 | 20 |  |  | 0.92857 | 6 |  | 32 | 12
|  | d | 3 | 8 |  |  | 0.33333 | 5 |  | 35 | 27
|  | e | 7 | 6 |  | 1 |  | -1 |  | 42 | 36
|  | Totals | 42 |  | 0 |  |  | 31 |  | 139 | 75
[5 empty] | Current Day: | 10
|  |  | Process. | Due | Remain | CR | Critical |  |  | Flow | Days
|  | Job | Time | Date | Oper. | Sequence | Ratio | Slack | S/O | Time | Late
|  | a | 12 | 15 |  |  | 0.41667 | 3 |  | 12 | 0
|  | b | 6 | 24 |  |  | 2.3333 | 18 |  | 18 | 0
|  | c | 14 | 20 |  |  | 0.71429 | 6 |  | 32 | 12
|  | d | 3 | 8 |  | 2 |  | 5 |  | 35 | 27
|  | e | 7 | 6 |  | 1 |  | -1 |  | 42 | 36
|  | Totals | 42 |  | 0 |  |  | 31 |  | 139 | 75
[5 empty] | Current Day: | 22
|  |  | Process. | Due | Remain | CR | Critical |  |  | Flow | Days
|  | Job | Time | Date | Oper. | Sequence | Ratio | Slack | S/O | Time | Late
|  | a | 12 | 15 |  | 3 |  | 3 |  | 12 | 0
|  | b | 6 | 24 |  |  | 0.33333 | 18 |  | 18 | 0
|  | c | 14 | 20 |  |  | -0.14286 | 6 |  | 32 | 12
|  | d | 3 | 8 |  | 2 |  | 5 |  | 35 | 27
|  | e | 7 | 6 |  | 1 |  | -1 |  | 42 | 36
|  | Totals | 42 |  | 0 |  |  | 31 |  | 139 | 75
|  |  | Process. | Due | Remain | CR | Critical |  |  | Flow | Days
|  | Job | Time | Date | Oper. | Sequence | Ratio | Slack | S/O | Time | Late
|  | a | 12 | 15 |  | 3 |  | 3 |  | 12 | 0
|  | b | 6 | 24 |  | 5 |  | 18 |  | 18 | 0
|  | c | 14 | 20 |  | 4 |  | 6 |  | 32 | 12
|  | d | 3 | 8 |  | 2 |  | 5 |  | 35 | 27
|  | e | 7 | 6 |  | 1 |  | -1 |  | 42 | 36
|  | Totals | 42 |  | 0 |  |  | 31 |  | 139 | 75
Press CR
|  |  | Process. | Due | Remain | CR | Critical |  |  | Flow | Days
|  | Job | Time | Date | Oper. | Sequence | Ratio | Slack | S/O | Time | Late
|  | e | 7 | 6 |  | 1 |  | -1 |  | 7 | 1
|  | d | 3 | 8 |  | 2 |  | 5 |  | 10 | 2
|  | a | 12 | 15 |  | 3 |  | 3 |  | 22 | 7
|  | c | 14 | 20 |  | 4 |  | 6 |  | 36 | 16
|  | b | 6 | 24 |  | 5 |  | 18 |  | 42 | 18
|  | Totals | 42 |  | 0 |  |  | 31 |  | 117 | 44
|  | Method |  |  | CR
|  | Average Flow Time |  |  | 23.4
|  | Average Tardiness |  |  | 8.8
|  | Average Number of Jobs |  |  | 2.7857
3. | Job Sequencing
|  |  | Process. | Due | Remain | Critical |  |  | Flow | Days
|  | Job | Time | Date | Oper. | Ratio | Slack | S/O | Time | Late
|  | a | 12 | 15 |  | 1.25 | 3 |  | 12 | 0
|  | b | 6 | 24 |  | 4 | 18 |  | 18 | 0
|  | c | 14 | 20 |  | 1.4286 | 6 |  | 32 | 12
|  | d | 3 | 8 |  | 2.6667 | 5 |  | 35 | 27
|  | e | 7 | 6 |  | 0.85714 | -1 |  | 42 | 36
|  | Totals | 42 |  | 0 |  | 31 |  | 139 | 75
|  | Method |  |  | FCFS
|  | Average Flow Time |  |  | 27.8
|  | Average Tardiness |  |  | 15
|  | Average Number of Jobs |  |  | 3.3095
4. | Job Sequencing
|  |  | Process. | Due | Remain | Critical |  |  | Flow | Days
|  | Job | Time | Date | Oper. | Ratio | Slack | S/O | Time | Late
|  | C | 10 | 6 | 2 | 0.6 | -4 | -2 | 10 | 4
|  | B | 11 | 18 | 5 | 1.6364 | 7 | 1.4 | 21 | 3
|  | D | 16 | 23 | 4 | 1.4375 | 7 | 1.75 | 37 | 14
|  | A | 20 | 30 | 2 | 1.5 | 10 | 5 | 57 | 27
|  | Totals | 57 |  | 13 |  | 20 |  | 125 | 48
|  | Method |  |  | S/O
|  | Average Flow Time |  |  | 31.25
|  | Average Tardiness |  |  | 12
|  | Average Number of Jobs |  |  | 2.193
5. | Johnson's Rule
| Step 1 - Fill in jobs and times: | [5 empty] | Resulting schedule:
|  | Job | Time1 | Time2 |  |  | Job | Start 1 | Done 1 | Start 2 | Done 2 | Idle 2
|  | a | 2.5 | 4.2 |  |  | c | 0 | 2.2 | 2.2 | 5.2 | 2.2
|  | b | 3.8 | 1.5 |  |  | a | 2.2 | 4.7 | 5.2 | 9.4 | 0
|  | c | 2.2 | 3 |  |  | d | 4.7 | 10.5 | 10.5 | 14.5 | 1.1
|  | d | 5.8 | 4 |  |  | e | 10.5 | 15 | 15 | 17 | 0.5
|  | e | 4.5 | 2 |  |  | b | 15 | 18.8 | 18.8 | 20.3 | 1.8
[8 empty] | 18.8 | 18.8 | 20.3 | 20.3 | 0
[8 empty] | 18.8 | 18.8 | 20.3 | 20.3 | 0
[7 empty] | Idle time-> |  | 1.5 |  |  | 5.6
Step 2 - Assign job order:
|  | a |  |  |  | c | a | d | e | b
b
c
d
e