## Chapter 18
Templates to accompany Operations Management, Seventh Edition
created by Lee Tangedahl, The University of Montana
Copyright © 2001 by The McGraw Hill Companies, Inc.
All rights Reserved.
Chapter Eighteen - Project Management
| Templates: | Pert/CPM with Deterministic Time Estimates
Pert/CPM, Probabilistic Time Estimates
Pert/CPM, Probabilistic Completion Time
Time-Cost Tradeoffs: Crashing
Examples
Solved Problems
See Instructions template for complete instructions.

## PERT, Deterministic
Pert/CPM with Deterministic Time Estimates
Note: use AOA notation with ascending nodes numbers from beginning to end.
| Activity | Start | End | Time | ES | EF | LF | LS | Slack
| a1 | 1 | 2 | 8 | 0 | 8 | 8 | 0 | 0
| a2 | 2 | 4 | 6 | 8 | 14 | 16 | 10 | 2
| a3 | 1 | 3 | 4 | 0 | 4 | 10 | 6 | 6
| a4 | 3 | 5 | 9 | 4 | 13 | 19 | 10 | 6
| a5 | 2 | 5 | 11 | 8 | 19 | 19 | 8 | 0
| a6 | 4 | 5 | 3 | 14 | 17 | 19 | 16 | 2
| a7 | 5 | 6 | 1 | 19 | 20 | 20 | 19 | 0

## PERT, Probabilistic
Pert/CPM, Probabilistic Time Estimates
Note: use AOA notation with ascending nodes numbers from beginning to end.
| Activity | Start | End | a | m | b | Var | E(T) | ES | EF | LF | LS | Slack
| a | 1 | 2 | 1 | 3 | 4 | 0.25 | 2.8333 | 0 | 2.8333 | 8.8333 | 6 | 6
| b | 2 | 5 | 2 | 4 | 6 | 0.44444 | 4 | 2.8333 | 6.8333 | 12.8333 | 8.8333 | 6
| c | 5 | 8 | 2 | 3 | 5 | 0.25 | 3.1667 | 6.8333 | 10 | 16 | 12.8333 | 6
| d | 1 | 3 | 3 | 4 | 5 | 0.11111 | 4 | 0 | 4 | 4 | 0 | 0
| e | 3 | 6 | 3 | 5 | 7 | 0.44444 | 5 | 4 | 9 | 9 | 4 | 0
| f | 6 | 8 | 5 | 7 | 9 | 0.44444 | 7 | 9 | 16 | 16 | 9 | 0
| g | 1 | 4 | 2 | 3 | 6 | 0.44444 | 3.3333 | 0 | 3.3333 | 5.8333 | 2.5 | 2.5
| h | 4 | 7 | 4 | 6 | 8 | 0.44444 | 6 | 3.3333 | 9.3333 | 11.8333 | 5.8333 | 2.5
| i | 7 | 8 | 3 | 4 | 6 | 0.25 | 4.1667 | 9.3333 | 13.5 | 16 | 11.8333 | 2.5

## PERT, Completion
Pert/CPM, Probabilistic Completion Time
|  | Path | Expected Times |  |  |  |  | E(t) | Variances |  |  | spath | Probability | 12.5 | 0.00087268
| 1 | 1-2-5-8 | 2.8333 | 4 | 3.1667 |  |  | 10 | 0.25 | 0.44444 | 0.25 | 0.97183 | 1 | 13.2 | 0.0079155
| 2 | 1-3-6-8 | 4 | 5 | 7 |  |  | 16 | 0.11111 | 0.44444 | 0.44444 | 1 | 0.84134 | 13.9 | 0.043984
| 3 | 1-4-7-8 | 3.3333 | 6 | 4.1667 |  |  | 13.5 | 0.44444 | 0.44444 | 0.25 | 1.0672 | 0.99948 | 14.6 | 0.14973
| 4 | [12 empty] | 15.3 | 0.31225
| 5 | [12 empty] | 16 | 0.39894
| 6 | [12 empty] | 16.7 | 0.31225
| 7 | [12 empty] | 17.4 | 0.14973
| 8 | [12 empty] | 18.1 | 0.043984
[7 empty] | Projected Completion Time: | 17 |  |  |  | Probability of Completion: | 0.84091 | 18.8 | 0.0079155
[14 empty] | 19.5 | 0.00087268
[14 empty] | 17 |  | 0
[14 empty] | 17 |  | 0.39894
[14 empty] | 6.2648 | 46 | 0
|  | Probability of completion for single path: | [11 empty] | 19.7352 | 19.7352 | 0
|  |  | Path |  | E(t) | spath | Probability
|  | 2 | 1-3-6-8 |  | 16 | 1 | 0.84134

## PERT, Crashing
Time-Cost Tradeoffs: Crashing
| Notes: | use AOA notation with ascending nodes numbers from beginning to end.
press Solve after each "crashing" entry.
[11 empty] | Project Completion Time: | 17
[11 empty] | Crashing Cost: | 1700
|  |  |  | Normal | Crashing
| Activity | Start | End | Time | Time | Cost | Time | ES | EF | LF | LS | Slack
| a | 1 | 2 | 6 |  |  | 6 | 0 | 6 | 6 | 0 | 0
| b | 2 | 5 | 10 |  |  | 10 | 6 | 16 | 16 | 6 | 0
| c | 1 | 3 | 5 | 1 | 300 | 4 | 0 | 4 | 4 | 0 | 0
| d | 3 | 4 | 4 |  |  | 4 | 4 | 8 | 8 | 4 | 0
| e | 4 | 5 | 9 | 1 | 600 | 8 | 8 | 16 | 16 | 8 | 0
| f | 5 | 6 | 2 | 1 | 800 | 1 | 16 | 17 | 17 | 16 | 0

## Examples
Chapter 18 - Examples
2-4. | Pert/CPM with Deterministic Time Estimates
Note: use AOA notation with ascending nodes numbers from beginning to end.
|  | Activity | Start | End | Time | ES | EF | LF | LS | Slack
|  | a1 | 1 | 2 | 8 | 0 | 8 | 8 | 0 | 0
|  | a2 | 2 | 4 | 6 | 8 | 14 | 16 | 10 | 2
|  | a3 | 1 | 3 | 4 | 0 | 4 | 10 | 6 | 6
|  | a4 | 3 | 5 | 9 | 4 | 13 | 19 | 10 | 6
|  | a5 | 2 | 5 | 11 | 8 | 19 | 19 | 8 | 0
|  | a6 | 4 | 5 | 3 | 14 | 17 | 19 | 16 | 2
|  | a7 | 5 | 6 | 1 | 19 | 20 | 20 | 19 | 0
5. | Pert/CPM, Probabilistic Time Estimates
Note: use AOA notation with ascending nodes numbers from beginning to end.
|  | Activity | Start | End | a | m | b | Var | E(T) | ES | EF | LF | LS | Slack
|  | a | 1 | 2 | 1 | 3 | 4 | 0.25 | 2.8333 | 0 | 2.8333 | 8.8333 | 6 | 6
|  | b | 2 | 5 | 2 | 4 | 6 | 0.44444 | 4 | 2.8333 | 6.8333 | 12.8333 | 8.8333 | 6
|  | c | 5 | 8 | 2 | 3 | 5 | 0.25 | 3.1667 | 6.8333 | 10 | 16 | 12.8333 | 6
|  | d | 1 | 3 | 3 | 4 | 5 | 0.11111 | 4 | 0 | 4 | 4 | 0 | 0
|  | e | 3 | 6 | 3 | 5 | 7 | 0.44444 | 5 | 4 | 9 | 9 | 4 | 0
|  | f | 6 | 8 | 5 | 7 | 9 | 0.44444 | 7 | 9 | 16 | 16 | 9 | 0
|  | g | 1 | 4 | 2 | 3 | 6 | 0.44444 | 3.3333 | 0 | 3.3333 | 5.8333 | 2.5 | 2.5
|  | h | 4 | 7 | 4 | 6 | 8 | 0.44444 | 6 | 3.3333 | 9.3333 | 11.8333 | 5.8333 | 2.5
|  | i | 7 | 8 | 3 | 4 | 6 | 0.25 | 4.1667 | 9.3333 | 13.5 | 16 | 11.8333 | 2.5
6. | Pert/CPM, Probabilistic Completion Time
|  |  | Path | Expected Times |  |  |  |  | E(t) | Variances |  |  |  |  | spath | Probability
|  | 1 | 1-2-5-8 | 2.8333 | 4 | 3.1667 |  |  | 10 | 0.25 | 0.44444 | 0.25 |  |  | 0.97183 | 1
|  | 2 | 1-3-6-8 | 4 | 5 | 7 |  |  | 16 | 0.11111 | 0.44444 | 0.44444 |  |  | 1 | 0.84134
|  | 3 | 1-4-7-8 | 3.3333 | 6 | 4.1667 |  |  | 13.5 | 0.44444 | 0.44444 | 0.25 |  |  | 1.0672 | 0.99948
4
5
6
7
8
[8 empty] | Projected Completion Time: | 17 | [5 empty] | Probability of Completion: | 0.84091
7. | Time-Cost Tradeoffs: Crashing
|  | Notes: | use AOA notation with ascending nodes numbers from beginning to end.
press Solve after each "crashing" entry.
[12 empty] | Project Completion Time: | 20
[12 empty] | Crashing Cost: | 0
[5 empty] | Normal | Crashing
|  | Activity | Start | End | Time | Time | Cost | Time | ES | EF | LF | LS | Slack
|  | a | 1 | 2 | 6 |  |  | 6 | 0 | 6 | 8 | 2 | 2
|  | b | 2 | 5 | 10 |  |  | 10 | 6 | 16 | 18 | 8 | 2
|  | c | 1 | 3 | 5 |  |  | 5 | 0 | 5 | 5 | 0 | 0
|  | d | 3 | 4 | 4 |  |  | 4 | 5 | 9 | 9 | 5 | 0
|  | e | 4 | 5 | 9 |  |  | 9 | 9 | 18 | 18 | 9 | 0
|  | f | 5 | 6 | 2 |  |  | 2 | 18 | 20 | 20 | 18 | 0
[12 empty] | Project Completion Time: | 19
[12 empty] | Crashing Cost: | 300
[5 empty] | Normal | Crashing
|  | Activity | Start | End | Time | Time | Cost | Time | ES | EF | LF | LS | Slack
|  | a | 1 | 2 | 6 |  |  | 6 | 0 | 6 | 7 | 1 | 1
|  | b | 2 | 5 | 10 |  |  | 10 | 6 | 16 | 17 | 7 | 1
|  | c | 1 | 3 | 5 | 1 | 300 | 4 | 0 | 4 | 4 | 0 | 0
|  | d | 3 | 4 | 4 |  |  | 4 | 4 | 8 | 8 | 4 | 0
|  | e | 4 | 5 | 9 |  |  | 9 | 8 | 17 | 17 | 8 | 0
|  | f | 5 | 6 | 2 |  |  | 2 | 17 | 19 | 19 | 17 | 0
[12 empty] | Project Completion Time: | 18
[12 empty] | Crashing Cost: | 900
[5 empty] | Normal | Crashing
|  | Activity | Start | End | Time | Time | Cost | Time | ES | EF | LF | LS | Slack
|  | a | 1 | 2 | 6 |  |  | 6 | 0 | 6 | 6 | 0 | 0
|  | b | 2 | 5 | 10 |  |  | 10 | 6 | 16 | 16 | 6 | 0
|  | c | 1 | 3 | 5 | 1 | 300 | 4 | 0 | 4 | 4 | 0 | 0
|  | d | 3 | 4 | 4 |  |  | 4 | 4 | 8 | 8 | 4 | 0
|  | e | 4 | 5 | 9 | 1 | 600 | 8 | 8 | 16 | 16 | 8 | 0
|  | f | 5 | 6 | 2 |  |  | 2 | 16 | 18 | 18 | 16 | 0
[12 empty] | Project Completion Time: | 17
[12 empty] | Crashing Cost: | 1700
[5 empty] | Normal | Crashing
|  | Activity | Start | End | Time | Time | Cost | Time | ES | EF | LF | LS | Slack
|  | a | 1 | 2 | 6 |  |  | 6 | 0 | 6 | 6 | 0 | 0
|  | b | 2 | 5 | 10 |  |  | 10 | 6 | 16 | 16 | 6 | 0
|  | c | 1 | 3 | 5 | 1 | 300 | 4 | 0 | 4 | 4 | 0 | 0
|  | d | 3 | 4 | 4 |  |  | 4 | 4 | 8 | 8 | 4 | 0
|  | e | 4 | 5 | 9 | 1 | 600 | 8 | 8 | 16 | 16 | 8 | 0
|  | f | 5 | 6 | 2 | 1 | 800 | 1 | 16 | 17 | 17 | 16 | 0

## Solved Problems
Chapter 18 - Solved Problems
1. | Pert/CPM with Deterministic Time Estimates
Note: use AOA notation with ascending nodes numbers from beginning to end.
|  | Activity | Start | End | Time | ES | EF | LF | LS | Slack
|  | a | 1 | 2 | 5 | 0 | 5 | 5 | 0 | 0
|  | b | 2 | 6 | 7 | 5 | 12 | 15 | 8 | 3
|  | c | 2 | 5 | 8 | 5 | 13 | 13 | 5 | 0
|  | d | 5 | 6 | 2 | 13 | 15 | 15 | 13 | 0
|  | e | 1 | 3 | 3 | 0 | 3 | 19 | 16 | 16
|  | f | 3 | 8 | 6 | 3 | 9 | 25 | 19 | 16
|  | g | 1 | 4 | 1 | 0 | 1 | 14 | 13 | 13
|  | h | 4 | 7 | 2 | 1 | 3 | 16 | 14 | 13
|  | i | 6 | 8 | 10 | 15 | 25 | 25 | 15 | 0
|  | k | 7 | 9 | 17 | 3 | 20 | 33 | 16 | 13
|  | m | 8 | 9 | 8 | 25 | 33 | 33 | 25 | 0
2. | Pert/CPM with Deterministic Time Estimates
Note: use AOA notation with ascending nodes numbers from beginning to end.
|  | Activity | Start | End | Time | ES | EF | LF | LS | Slack
|  | 1-2 | 1 | 2 | 4 | 0 | 4 | 11 | 7 | 7
|  | 2-5 | 2 | 5 | 6 | 4 | 10 | 17 | 11 | 7
|  | 2-4 | 2 | 4 | 2 | 4 | 6 | 14 | 12 | 8
|  | 1-3 | 1 | 3 | 9 | 0 | 9 | 9 | 0 | 0
|  | 3-4 | 3 | 4 | 5 | 9 | 14 | 14 | 9 | 0
|  | 4-5 | 4 | 5 | 3 | 14 | 17 | 17 | 14 | 0
3. | Pert/CPM, Probabilistic Completion Time
|  |  | Path | Expected Times |  |  |  |  | E(t) | Variances |  |  |  | spath | Probability
|  | 1 | 1-2-5-8 | 16 | 11 | 24 |  |  | 51 | 0.69 | 0.69 | 0.11 |  | 1.2207 | 0.20633
|  | 2 | 1-2-6-8 | 5 | 18 | 26 |  |  | 49 | 0 | 0.25 | 0.11 |  | 0.6 | 0.95221
|  | 3 | 1-3-4-7-8 | 5 | 10 | 14 | 12 |  | 41 | 0 | 0.25 | 0.36 | 0.11 | 0.84853 | 1
4
5
6
7
8
[8 empty] | Projected Completion Time: | 50 |  |  |  |  | Probability of Completion: | 0.19647
4. | Time-Cost Tradeoffs: Crashing
|  | Notes: | use AOA notation with ascending nodes numbers from beginning to end.
press Solve after each "crashing" entry.
[12 empty] | Project Completion Time: | 24
[12 empty] | Crashing Cost: | 0
[5 empty] | Normal | Crashing
|  | Activity | Start | End | Time | Time | Cost | Time | ES | EF | LF | LS | Slack
|  | a | 1 | 2 | 10 |  |  | 10 | 0 | 10 | 10 | 0 | 0
|  | b | 2 | 5 | 14 |  |  | 14 | 10 | 24 | 24 | 10 | 0
|  | c | 1 | 3 | 13 |  |  | 13 | 0 | 13 | 18 | 5 | 5
|  | d | 3 | 5 | 6 |  |  | 6 | 13 | 19 | 24 | 18 | 5
|  | e | 1 | 4 | 15 |  |  | 15 | 0 | 15 | 16 | 1 | 1
|  | f | 4 | 5 | 8 |  |  | 8 | 15 | 23 | 24 | 16 | 1
[12 empty] | Project Completion Time: | 23
[12 empty] | Crashing Cost: | 3000
[5 empty] | Normal | Crashing
|  | Activity | Start | End | Time | Time | Cost | Time | ES | EF | LF | LS | Slack
|  | a | 1 | 2 | 10 |  |  | 10 | 0 | 10 | 10 | 0 | 0
|  | b | 2 | 5 | 14 | 1 | 3000 | 13 | 10 | 23 | 23 | 10 | 0
|  | c | 1 | 3 | 13 |  |  | 13 | 0 | 13 | 17 | 4 | 4
|  | d | 3 | 5 | 6 |  |  | 6 | 13 | 19 | 23 | 17 | 4
|  | e | 1 | 4 | 15 |  |  | 15 | 0 | 15 | 15 | 0 | 0
|  | f | 4 | 5 | 8 |  |  | 8 | 15 | 23 | 23 | 15 | 0
[12 empty] | Project Completion Time: | 22
[12 empty] | Crashing Cost: | 9000
[5 empty] | Normal | Crashing
|  | Activity | Start | End | Time | Time | Cost | Time | ES | EF | LF | LS | Slack
|  | a | 1 | 2 | 10 |  |  | 10 | 0 | 10 | 10 | 0 | 0
|  | b | 2 | 5 | 14 | 2 | 7000 | 12 | 10 | 22 | 22 | 10 | 0
|  | c | 1 | 3 | 13 |  |  | 13 | 0 | 13 | 16 | 3 | 3
|  | d | 3 | 5 | 6 |  |  | 6 | 13 | 19 | 22 | 16 | 3
|  | e | 1 | 4 | 15 |  |  | 15 | 0 | 15 | 15 | 0 | 0
|  | f | 4 | 5 | 8 | 1 | 2000 | 7 | 15 | 22 | 22 | 15 | 0
[12 empty] | Project Completion Time: | 21
[12 empty] | Crashing Cost: | 19000
[5 empty] | Normal | Crashing
|  | Activity | Start | End | Time | Time | Cost | Time | ES | EF | LF | LS | Slack
|  | a | 1 | 2 | 10 |  |  | 10 | 0 | 10 | 10 | 0 | 0
|  | b | 2 | 5 | 14 | 3 | 11000 | 11 | 10 | 21 | 21 | 10 | 0
|  | c | 1 | 3 | 13 |  |  | 13 | 0 | 13 | 15 | 2 | 2
|  | d | 3 | 5 | 6 |  |  | 6 | 13 | 19 | 21 | 15 | 2
|  | e | 1 | 4 | 15 | 1 | 6000 | 14 | 0 | 14 | 14 | 0 | 0
|  | f | 4 | 5 | 8 | 1 | 2000 | 7 | 14 | 21 | 21 | 14 | 0