Chapter 8

Timeliness

Answers to Odd-Numbered End-of-Chapter Problems

1.

3.

5.

| Client | Estimated Completion Time | Due Date | Expected Completion Date | Lateness |
| --- | --- | --- | --- | --- |
| The Shores | 4 | 5 | 4 | 0 |
| Nation-beat | 6 | 8 | 10 | 2 |
| Free News | 4 | 15 | 14 | 0 |
| City Times | 3 | 17 | 17 | 0 |
| The Star | 5 | 19 | 22 | 3 |
| Monthly Press | 2 | 23 | 24 | 1 |
| Gossip | 4 | 27 | 28 | 1 |
|  |  |  | total days late | 7 |
|  |  |  | # of jobs late | 4 |
|  |  |  | avg. lateness | 1 |

7.

| Client | Estimated Time | Due Date | Expected Completion Date | Lateness |
| --- | --- | --- | --- | --- |
| Brown | 2 | 4 | 2 | 0 |
| Dewar | 3 | 8 | 5 | 0 |
| Smith | 4 | 6 | 9 | 3 |
| Walker | 5 | 11 | 14 | 3 |
|  |  |  | total days late | 6 |
|  |  |  | number of jobs late | 2 |
|  |  |  | average lateness | 1.5 |

The longer jobs are most likely to be late, since they are put off until the end.

9.
a.

| SPT |  |  |  |  |
| --- | --- | --- | --- | --- |
| Order | Processing Time | Due Date | Completion | Lateness |
| 1 | 4 | 12 | 4 | 0 |
| 3 | 5 | 14 | 9 | 0 |
| 4 | 10 | 34 | 19 | 0 |
| 5 | 11 | 41 | 30 | 0 |
| 2 | 15 | 32 | 45 | 13 |

| EDD |  |  |  |  |
| --- | --- | --- | --- | --- |
| Order | Processing Time | Due Date | Completion | Lateness |
| 1 | 4 | 12 | 4 | 0 |
| 3 | 5 | 14 | 9 | 0 |
| 2 | 15 | 32 | 24 | 0 |
| 4 | 10 | 34 | 34 | 0 |
| 5 | 11 | 41 | 45 | 4 |

  - SPT average lateness = 2.6; EDD average lateness .8.  Both rules have 1 job late.

11.

|  | Route |  | Expected Clearing | Due Date | Completion | Late |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Time |  | (hours) | time |  |
|  | Fire to I90 | 1.5 |  | 2 | 1.5 | 0 |
|  | Police to I90 | 0.5 |  | 2 | 2 | 0 |
|  | Hospital to I90 | 2 |  | 3 | 4 | 1 |
|  | Main |  | 2 |  | 5 | 6 | 1 |
|  | University | 1 |  | 4 | 7 | 3 |
|  |  |  |  |  |  | avg late | 1 |
| SPT | Route |  | Expected Clearing | Due Date | Completion | Late |
|  |  |  | Time |  | (hours) | time |  |
|  | Police to I90 | 0.5 |  | 2 | 0.5 | 0 |
|  | University | 1 |  | 4 | 1.5 | 0 |
|  | Fire to I90 | 1.5 |  | 2 | 3 | 1 |
|  | Hospital to I90 | 2 |  | 3 | 5 | 2 |
|  | Main |  | 2 |  | 5 | 7 | 2 |
|  |  |  |  |  |  | avg late | 1 |
| EDD | Route |  | Expected Clearing | Due Date | Completion | Late |
|  |  |  | Time |  | (hours) | time |  |
|  | Fire to I90 | 1.5 |  | 2 | 1.5 | 0 |
|  | Police to I90 | 0.5 |  | 2 | 2 | 0 |
|  | Hospital to I90 | 2 |  | 3 | 4 | 1 |
|  | University | 1 |  | 4 | 5 | 1 |
|  | Main |  | 2 |  | 5 | 7 | 2 |
|  |  |  |  |  |  | avg late | 0.8 |

EDD gives lower average lateness (.8 vs 1). Both yield 3 jobs late.

13.

Critical ratio

| Client | Estimated Time | Due Date | Critical Ratio | Expected Completion | Lateness |
| --- | --- | --- | --- | --- | --- |
| Beta | 5 | 5 | 1 | 5 | 0 |
| Draw-it | 6 | 9 | 1.5 | 11 | 2 |
| AIM | 4 | 17 | 4.25 | 15 | 0 |
| E-notes | 3 | 15 | 5 | 18 | 3 |
| Coral | 2 | 13 | 6.5 | 20 | 7 |
|  |  |  |  | total days late | 12 |
|  |  |  |  | number of jobs late | 3 |
|  |  |  |  | average lateness | 2.4 |

Shortest Processing Time

| Client | Estimated Time | Due Date | Expected Completion Date | Lateness |
| --- | --- | --- | --- | --- |
| Coral | 2 | 13 | 2 | 0 |
| E-notes | 3 | 15 | 5 | 0 |
| AIM | 4 | 17 | 9 | 0 |
| Beta | 5 | 5 | 14 | 9 |
| Draw-it | 6 | 9 | 20 | 11 |
|  |  |  | total days late | 20 |
|  |  |  | number of jobs late | 2 |
|  |  |  | average lateness | 4 |

Earliest Due date

| Client | Estimated Time | Due Date | Expected Completion Date | Lateness |
| --- | --- | --- | --- | --- |
| Beta | 5 | 5 | 5 | 0 |
| Draw-it | 6 | 9 | 11 | 2 |
| Coral | 2 | 13 | 13 | 0 |
| E-notes | 3 | 15 | 16 | 1 |
| AIM | 4 | 17 | 20 | 3 |
|  |  |  | total days late | 6 |
|  |  |  | number of jobs late | 3 |
|  |  |  | average lateness | 1.2 |

EDD is best for average lateness and total number of days late.  SPT is best for number of jobs late.

15.

| Client | Order Arrival | Due Date | Estimated Completion Time | Number of Remaining Operations | Slack | Slack per remaining Operation |
| --- | --- | --- | --- | --- | --- | --- |
| Timmy Hendricks | 1 | 7 | 4 | 2 | 3 | 1.5 |
| Don Mathews | 2 | 11 | 6 | 4 | 5 | 1.25 |
| Moses Moreno | 3 | 21 | 8 | 4 | 13 | 3.25 |
| Pat Dylan | 4 | 16 | 2 | 4 | 14 | 3.5 |
| Edy Van Whalen | 5 | 17 | 5 | 4 | 12 | 3 |

17.

| Job ID |  | Total time | Total Time | Critical |
| --- | --- | --- | --- | --- |
|  |  | Required (hrs) | Until Due (hrs) | Ratio |
| 105 |  | 21 |  | 24 |  | 1.142857 |
| 103 |  | 16 |  | 24 |  | 1.5 |
| 102 |  | 14 |  | 26 |  | 1.857143 |
| 101 |  | 18 |  | 35 |  | 1.944444 |
| 104 |  | 10 |  | 20 |  | 2 |

19.

| x- | 30 |
| --- | --- |
| e- | 2.7183 |
| Avg arrival rate | 24 |
| P- | 3.63% |

21.

| x- | 40 |
| --- | --- |
| e- | 2.7183 |
| Avg arrival rate | 25 |
| P- | 0.14% |

23.

25.

| Activity | Early Start | Late Start | Early Finish | Late Finish | Slack |
| --- | --- | --- | --- | --- | --- |
| A | 0 | 0 | 3 | 3 | 0 |
| B | 3 | 15 | 9 | 21 | 12 |
| C | 3 | 4 | 13 | 14 | 1 |
| D | 3 | 3 | 17 | 17 | 0 |
| E | 17 | 17 | 23 | 23 | 0 |
| F | 13 | 14 | 22 | 23 | 1 |
| G | 17 | 21 | 19 | 23 | 4 |
| H | 23 | 23 | 27 | 27 | 0 |

The critical path is ADEH with a completion time of 27 days.

27.

| Activity ID | Activity | ES | EF | LS | LF | Slack |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Study Feasibility | 0 | 6 | 1 | 7 | 1 |
| 2 | Gather Information | 0 | 4 | 2 | 6 | 2 |
| 3 | Explore Options | 0 | 6 | 0 | 6 | 0 |
| 4 | Define Users | 4 | 5 | 6 | 7 | 1 |
| 5 | Narrow To One | 6 | 7 | 6 | 7 | 0 |
| 6 | Prototype | 7 | 17 | 7 | 17 | 0 |
| 7 | Internal Test | 17 | 22 | 20 | 25 | 3 |
| 8 | External Test | 17 | 25 | 17 | 25 | 0 |
| 9 | Measure Performance | 25 | 30 | 25 | 30 | 0 |
| 10 | Production | 30 | 55 | 30 | 55 | 0 |

3-5-6-8-9-10 is the critical path.

29.  The critical path is 1,2,4,5.

| Activity ID | Activity Description | Optimistic | Most Likely | Pessimistic | Te | Variance |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Preparation | 6.5 | 8.5 | 10.5 | 8.5 | 0.4444 |
| 2 | Preliminary | 3 | 5 | 7 | 5 | 0.4444 |
| 3 | Common Ground | 2 | 5 | 8 | 5 | 1.0000 |
| 4 | Issue at Hand | 8 | 10.5 | 13 | 10.5 | 0.6944 |
| 5 | Agreement | 2.5 | 4 | 7 | 4.25 | 0.5625 |

| Activity ID | Activity Description | Te | ES | EF | LS | LF | Slack |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Preparation | 8.5 | 0 | 8.5 | 0 | 8.5 | 0 |
| 2 | Preliminary | 5 | 8.5 | 13.5 | 8.5 | 13.5 | 0 |
| 3 | Common Ground | 5 | 13.5 | 18.5 | 19 | 24 | 5.5 |
| 4 | Issue at Hand | 10.5 | 13.5 | 24 | 13.5 | 24 | 0 |
| 5 | Agreement | 4.25 | 24 | 28.25 | 24 | 28.25 | 0 |

31.  The critical path is 1,2,4,5

| Activity ID | Activity Description | Optimistic | Most Likely | Pessimistic | Te | Variance |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Dress | 9 | 11 | 13 | 11 | 0.4444 |
| 2 | Warmup | 4 | 6 | 8 | 6 | 0.4444 |
| 3 | Stretch | 3 | 5 | 7 | 5 | 0.4444 |
| 4 | Assignments | 2 | 5 | 8 | 5 | 1.0000 |
| 5 | Pre-Game | 3 | 6 | 9 | 6 | 1.0000 |

| Activity ID | Activity Description | Te | ES | EF | LS | LF | Slack |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Dress | 3 | 0 | 11 | 0 | 11.0 | 0 |
| 2 | Warmup | 6 | 11 | 17 | 11 | 17.0 | 0 |
| 3 | Stretch | 5 | 11 | 16 | 12 | 17 | 1 |
| 4 | Assignments | 5 | 17 | 22 | 17 | 22 | 0 |
| 5 | Pre-Game | 6 | 22 | 28 | 22 | 28.00 | 0 |

| variance of critical path | 2.8888 |
| --- | --- |
| standard deviation |  | 1.6996 |

Z = (25-28)/1.6990 = about 4%

33.

Activity C is reduced by 1 day for $200

Activity A is reduced by 1 day for $250

Activity A is reduced by 1 day for $250

Activity F is reduced by 1 day for $350

Activity D is reduced by 1 day for $400

Cutting 5 days from the project costs a total of $1450

# Text boxes

5

10

15

10

10

10

0

10

20

30

Assistant

Manager

Director of

Concessions

Understand Client

Narrow Choices

Understand Industry

Investigate Areas

Weigh Costs

Present

A

D

E

C

B

J

H

G

I

F

1

2

3

4

5

6

7

8

9

10